## Universal Domination BurndownCh
Sprint | Issue | Tasks | Status | Start | Finish | Duration | Comments | Predecessors
Learn how to use this template
| AGILE PROJECT |  |  | 2017-05-22 | 2017-07-18 | 43d
Sprints |  |  |  | 2017-05-22 | 2017-07-18 | 43d
Sprint 1 | Build Splash screen | Task 1 | Complete | 2017-05-22 | 2017-06-09 | 15d
Sprint 1 | Design the static GUI | Task 2 | Complete | 2017-05-22 | 2017-06-09 | 15d
Sprint 1 | Design menu | Task 3 | Complete | 2017-05-22 | 2017-06-09 | 15d
Sprint 1 | Assign buttons in menu to scenes | Task 4 | Complete | 2017-05-22 | 2017-06-09 | 15d
Sprint 1 | Design login menu | Task 5 | Complete | 2017-05-22 | 2017-06-09 | 15d
Sprint 1 | Design sign-up menu | Task 6 | Complete | 2017-05-22 | 2017-06-09 | 15d
Sprint 1 | Link each scene to each other with buttons | Task 7 | Complete | 2017-06-10 | 2017-06-09 | 15d
Sprint 2 | Write the code/ function for Sign-in/up | Task 8 | No started | 2017-06-10 | 2017-07-18 | 27d
Sprint 3 | Build database for logins | Task 9 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the code/ function for Social media integration (Facebook sign-up/log-in) | Task 10 | No started | 2017-06-10 | 2017-07-18 | 27d
| Decide what needs to be in “Settings menu” and write code | Task 11 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the code/function for player | Task 12 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the code/function for player to enter the Lobby (public) | Task 13 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the class/ function for “Reinforce” | Task 14 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the class/ function for “Attack” | Task 15 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the class/ function for “Fortify” | Task 16 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the class/function for “Limit to 3 attacks per turn” | Task 17 | No started | 2017-06-10 | 2017-07-18 | 27d
| Write the code of function for “Limiting 4 players in each game” | Task 18 | No started | 2017-06-10 | 2017-07-18 | 27d
| Design countdown timer ---> sprint 2 | Task 19 | No started | 2017-06-10 | 2017-07-18 | 27d
| Design dice roll ----> sprint 2 | Task 20 | No started | 2017-06-10 | 2017-07-18 | 27d